## Sheet1
Group members: | Niranjan Marathe
Peter Chung
Software system: | Jedit
Modified classes: | org/gjt/sp/jedit/textarea/JEditTextArea.java
org/gjt/sp/jedit/textarea/TextArea.java
org/gjt/sp/jedit/actions.xml
org/gjt/sp/jedit/jedit_gui.props
Time spent on this change request: | 660 mins
Initiation | 30 min
Concept location | 480 min
Impact analysis | 60 min
Actualization | 60 min
Testing | 30 min
Process followed to implement the Change Request:
Initiation | Executed the following scenario a. Opened a text file large enough so that scroll bars are visible b. Edit -> Go To Line is used c. Go To Line menu has handle to the text area, so decided to explore that functionality
Concept location | 1. Search for Edit menu implementation.
2. Explored a list of classes like EnhancedMenuItem etc. to figure out how Edit and it's sub menu items are implemented.
3. Found out that jedit_gui.props is used to define the menu labels including Edit -> Go To Line
4. Figured out that jEdit is using command pattern for handling the menu clicks.
5. Searched for action definitions for the commands and found the actions.xml where menu commands and their actions are defined.
Impact analysis | 1. Marked the actions.xml file as impacted, because new action needs to be defined for "Toggle Scrollbars" menu.
2. Marked the file jedit_gui.props as impacted, because new menu item "Toggle Scrollbars" will be defined in this file.
3. The class TextArea is marked as impacted because it needs to be modified to expose the JScrollBar private variables for vertical and horizontal scroll bars.
4. Marked the class JEditTextArea as impacted because it needs to be modified to implement the action for "Toggle Scrollbars" menu under Edit menu.
5. The impact set is two java classes and two configuration files.
Actualization | 1. Modified jedit_gui.props to add a new menu "Toggle Scrollbars" under the Edit menu.
2. Modified actions.xml to add corresponding action for the "Toggle Scrollbars" menu.
3. Added a new method toggleScrollBars() to the JTextEditArea class to handle the "Toggle Scrollbars" action.
4. Added getters for the private variables to TextArea class for exposing JScrollBars.
Testing | Following test cases are created
1. Hide scrollbars if they are visible by clicking "Toggle Scrollbars".
2. Show scrollbars if they are hidden if "Toggle Scrollbars" is clicked.
3. Hide scrollbar if either horizontal or vertical is shown.
All tests passed.
Additional information
As you explore and modify the system, you will learn more and more about the classes of system. Construct an annotated UML diagram with all the classes you have visited and evolve it as you perform the change requests. The diagram could be hand drawn. Save a snapshot at the end of each phase of the change (picture or scan will also work). The annotations on the diagram should be free text, summarizing what you learned about each class. For example, you can write about a class what you think its main purpose is, or some specific opersation it is responsible for and which methods/attributes are the ones implementing that specific operation. Also, you may annotate relationships between classed. For example, if there is a method call between two classes that you understand, you may describe the purpose of that relationship.